## TestCase
| Product Name |  | Fabrilife | TC Start Date | 17/9/2022 | TC Execution Start Date | 17/9/2022 |  |  |  | TEST CASE
| Module Name |  | SignUP, login | TC End Date | 22/9/2022 | TC Execution End Date | 22/09/2021 |  |  |  | PASS | 60
|  |  |  | Test Case Developed By | Anushka Azad | Browser (tested) | 1 |  |  |  | FAIL | 10
| Developer Name (TL) |  | x | Test Case Reviewed By |  | Performance (tested) | No |  |  |  | Not Executed | 0
[11 empty] | Out of Scope | 0
[11 empty] | TOTAL | 70
#SL | Module | Type of Testing | Features | Test Cases | test Data | Reporducing Steps | Exepected Result | Actual Result | Bug Screen Shot | Dev Comments | Final Status | Remarks
TC-001 | User MANGEMENT | Non Functional Testing | signUp | Check all the text box alignment ,ratio, colours . | N/A | 1.go to url with broswer 2.then login option comes with dropdown where 3 options come which is login, register, ordertrack. 3.register button click | all text boxes, ratio ,colour ,buttons, dropdown are perfect | UI should be perfect |  |  | Passed
TC-002 |  |  |  | spelling mistake or grammatical mistake | N/A | 1.1.go to url with broswer. 2.then login option comes with dropdown where 3 options come which is login, register, ordertrack. 3.register button click . | page should not contain any grammatical mistake. | not found any mistake. |  |  | Passed
TC-003 |  | Functional Testing | Sign UP | checking the registration from without filing any data | N/A | 1.1.go to url with broswer. 2.then login option comes with dropdown where 3 options come which is login, register, ordertrack. 3.register button click . 4. Do not enter any value in the field. 5.Click on the Register button. | It should not be register and show a message in every field to fill up this field | Not registered but showing a warning message. |  |  | Passed
TC-004 |  | Functional |  | Check user should Register by filling all the required fields with vaild infromation | name-Anushka Azad email-anushkaazad6@gmail.com phn number- 01757162434 password-anus12345 confirm password- anus12345 | 1.go to url with broswer. 2.then login option comes with dropdown where 3 options come which is login, register, ordertrack. 3.register button click . 4. fill the fields with valid info. 5.Click on the Register button. | should be registered and otp message showed | user registration works proparly and shows a otp message. |  |  | Passed
TC-005 |  | functional |  | checking Otp vailadation | 796899 | 1.go to url with broswer. 2.then login option comes with dropdown where 3 options come which is login, register, ordertrack. 3.register button click . 4. fill the fields with valid info. 5.Click on the Register button. | should send message on phone number | found as per expected |  |  | Passed
TC-006 |  | functional |  | checking otp with empty value |  | 1.go to url with broswer. 2.then login option comes with dropdown where 3 options come which is login, register, ordertrack. 3.register button click . 4. fill the fields with valid info. 5.Click on the Register button. | should not registered | found as per expected |  |  | Passed
TC-007 |  | functional |  | checking otp with time validation | N/A | 1.go to url with broswer. 2.then login option comes with dropdown where 3 options come which is login, register, ordertrack. 3.register button click . 4. fill the fields with valid info. 5.Click on the Register button. | should be showed time limitation with 60sec | found as per expected |  |  | Passed
TC-008 |  | functional |  | takes otp after time limit | 352915 | 1.go to url with broswer. 2.then login option comes with dropdown where 3 options come which is login, register, ordertrack. 3.register button click . 4. fill the fields with valid info. 5.Click on the Register button. | should not take otp code | takes otp code after time limit | https://prnt.sc/SEahKLjYk4wf |  | Failed
TC-009 |  | functional |  | clicking resend button hyperlink on |  | 1.go to url with broswer. 2.then login option comes with dropdown where 3 options come which is login, register, ordertrack. 3.register button click . 4. fill the fields with valid info. 5.Click on the Register button. | should be resend otp code | as expected |  |  | Passed
TC-010 |  | functional |  | checking otp code can not be used double |  | 1.go to url with broswer. 2.then login option comes with dropdown where 3 options come which is login, register, ordertrack. 3.register button click . 4. fill the fields with valid info. 5.Click on the Register button. | should not take it used otp code | as expected |  |  | Passed
TC-011 |  | functional |  | check resend button click |  | 1.go to url with broswer. 2.then login option comes with dropdown where 3 options come which is login, register, ordertrack. 3.register button click . 4. fill the fields with valid info. 5.Click on the Register button. | should not resend button cilckable ,it gives time limit. | as expected |  |  | Passed
TC-012 |  | functional |  | check the timer of resend OTP |  | 1.go to url with broswer. 2.then login option comes with dropdown where 3 options come which is login, register, ordertrack. 3.register button click . 4. fill the fields with valid info. 5.Click on the Register button. | should start a new resend timer | showed the previous timer after clicking the cross bar | https://prnt.sc/lPHYR0joBOvU , https://prnt.sc/dLeYVpr02x9j |  | Failed
TC-013 |  | functional |  | check all texts are readable | N/A | 1.go to url with broswer. 2.then login option comes with dropdown where 3 options come which is login, register, ordertrack. 3.register button click . 4. fill the fields with valid info. 5.Click on the Register button. | texts should be reable | found as per expected |  |  | Passed
TC-014 |  | positive |  | name field with empty value | N/A | 1.go to url with broswer. 2.then login 3.click on register button click . | warning message should be showed. | found as per expected |  |  | Passed
TC-0015 |  | negative |  | Name field with preceding space inputs | anushka | 1.go to url with broswer. 2.then login 3.click on register button click . | should not take preceding space | takes preceding space | https://prnt.sc/G8hX-7csAv-J |  | failed
TC-016 |  | negative |  | Name field with only special characters(without alphabets) | #@12 | 1.go to url with broswer. 2.then login 3.click on register button click | name should not start with special characters | takes specical characters | https://prnt.sc/NwdeXyLWneBl |  | failed
TC-017 |  | negative |  | Name field with interger | 12345 | 1.go to url with broswer. 2.then login 3.click on register button click . | should not take only interger and should show a warning message | takes only integer and should not show a warning message | https://prnt.sc/xJP5aXOM6bL1 |  | failed
TC-018 |  | positive |  | Email filed validation checking | anushkaazad6@gmail.com | 1.go to url with broswer. 2.then login 3.click on register button click | should take vaild gmail address . | as expected |  |  | Passed
TC-019 |  | postive |  | Email field with empty input | N/A | 1.go to url with broswer. 2.then login 3.click on register button click | Should show a warning message for the blank field. | as expected |  |  | Passed
TC-020 |  | negative |  | Email field with invalid mail address | shlaskar10@abc123 | 1.go to url with broswer. 2.then login 3.click on register button click . | Should show a warning message | as expected |  |  | Passed
TC-021 |  | negative |  | Email field with numbers | 1234567 | 1.go to url with broswer. 2.then login 3.click on register button click . | should show a warning message which is please include an '@' in the email address. '1234567' is missing an '@' | as expected |  |  | Passed
TC-022 |  | negative |  | Email field with only alphabets | abcd | 1.go to url with broswer. 2.then login 3.click on register button click . | An error message should appear under email field | as expected |  |  | Passed
TC-023 |  | negative |  | checking Email field with already existed mail id | anushkaazad6@gmail.com | 1.go to url with broswer. 2.then login 3.click on register button click . | an error message should appear under email field | as expected |  |  | Passed
TC-024 |  | negative |  | Phone field with empty input | N/A | 1.go to url with broswer. 2.then login 3.click on register button click . | An error message should appear under phone number field | as expected |  |  | Passed
TC-025 |  | negative |  | Phone field with alphabets | abcdefgh | 1.go to url with broswer. 2.then login 3.click on register button click . | An error message should appear under phone number field | as expected an error message which requests to fill the given format |  |  | Passed
TC-026 |  | negative |  | Phone field with alpha-numeric | abc123 | 1.go to url with broswer. 2.then login 3.click on register button click . | An error message should appear under phone number field | as expected |  |  | Passed
TC-027 |  | negative |  | Phone number field with invalid country code | 88123457890 | 1.go to url with broswer. 2.then login 3.click on register button click . | An error message should appear under phone number field | as expected |  |  | Passed
TC-028 |  | boundary |  | Phone number field with 10 digits | 175716243 | 1.go to url with broswer. 2.then login 3.click on register button click . | An error message should appear under phone number field | as expected |  |  | Passed
TC-029 |  | boundary |  | Phone number field with 12 digits | 17571624345 | 1.go to url with broswer. 2.then login 3.click on register button click . | An error message should appear under phone number field | as expected |  |  | Passed
TC-030 |  | negative |  | Phone number field with space in between valid input | 01757162 434 | 1.go to url with broswer. 2.then login 3.click on register button click . | An error message should appear under phone number field | as expected |  |  | Passed
TC-031 |  | negative |  | Password field empty | N/A | 1.go to url with broswer. 2.then login 3.click on register button click . | An error message should appear under password field | as expected |  |  | Passed
TC-032 |  | positive |  | Password field with alphabets | anushkaa | 1.go to url with broswer. 2.then login 3.click on register button click . | should accept | as expected |  |  | Passed
TC-033 |  | positive |  | Password field with special characters | #@!&(* | 1.go to url with broswer. 2.then login 3.click on register button click . | should accept | as expected |  |  | Passed
TC-034 |  | positive |  | Password field with numbers | 12345678 | 1.go to url with broswer. 2.then login 3.click on register button click . | should accept | as expected |  |  | Passed
TC-035 |  | positive |  | Password field with lower and upper case alphabets | anuuADGG | 1.go to url with broswer. 2.then login 3.click on register button click . | should accept | as expected |  |  | Passed
TC-036 |  | positive |  | Password field with space inputs |  | 1.go to url with broswer. 2.then login 3.click on register button click . | should accept | as expected |  |  | Passed
TC-037 |  | boundary |  | password field lower and upper boundray (8 to infinity) | 1757162434 | 1.go to url with broswer. 2.then login 3.click on register button click . | should accept | as expected |  |  | Passed
TC-038 |  | functional |  | password should be masked |  | 1.go to url with broswer. 2.then login 3.click on register button click . | expected not to show the password when user are typing | found as expected |  |  | Passed
TC-039 |  | functional |  | Clicking pick icon on password field | 12345678 | 1.go to url with broswer. 2.then login 3.click on register button click . | Written password should be visible | not found as expected | https://prnt.sc/5Mnm--5wD3jU |  | Failed
TC-040 |  | positive |  | confirmed password validation | 12345678 | 1.go to url with broswer. 2.then login 3.click on register button click . | should accept | found as expected |  |  | Passed
TC-041 |  | functional |  | hovering the mouse should highlight the button |  | 1.go to url with broswer. 2.then login 3.click on register button click . | highlights the register button | as expected |  |  | Passed
TC-042 |  | functional |  | siging up with facebook | N/A | 1.go to url with broswer. 2.then login 3.click on register button click . | should be logged in | error accessing app type message showed | https://prnt.sc/7pv2W1D2DXhT |  | Failed
TC-043 |  | Non -functional | Sign In | Verifying whether Sign In page appears | N/A | 1.go to url with browser 2. Click on "Sign In" button. 3. A new page will appear having Sign In button. | A Sign In UI should appear | as expected |  |  | Passed
TC-044 |  |  |  | Grammatical or spelling mistake on Sign In page | N/A | 1.go to url with browser 2. Click on "Sign In" button. 3. A new page will appear having Sign In button. | should not found any grammatical or spelling problem | as expected |  |  | Passed
TC-045 |  |  |  | checking all text boxes, size, font, aligment for sign in page | N/A | 1.go to url with browser 2. Click on "Sign In" button. 3. A new page will appear having Sign In button. | all text boxes are size ,font colour are ok | as expected |  |  | Passed
TC-046 |  | positive | Sign IN | checking with valid email id and password | anushkaazad6@gmail.com anu12345 | 1.go to url with browser 2. Click on "Sign In" button. 3. A new page will appear having Sign In button. | user should logged in | as expected |  |  | Passed
TC-047 |  | negative |  | checking with invalid email id and valid password | anush@com anu12345 | 1.go to url with browser 2. Click on "Sign In" button. 3. A new page will appear having Sign In button. | an error message showed | as expected |  |  | Passed
TC-048 |  | negative |  | checking with valid email id and invaild password | anushkaazad6@gmail.com 12345678 | 1.go to url with browser 2. Click on "Sign In" button. 3. A new page will appear having Sign In button. | an error message should be showed | don't show any an error message | https://prnt.sc/FIwBi9w9OoB8 |  | Failed
TC-049 |  | negative |  | checking with invalid email id and invaild password | anushkaazad6@com asd12345 | 1.go to url with browser 2. Click on "Sign In" button. 3. A new page will appear having Sign In button. | an error message should be showed | as expected |  |  | Passed
TC-050 |  | functional |  | checking Remember Me option clickable or not | N/A | 1.go to url with browser 2. Click on "Sign In" button. 3. A new page will appear having Sign In button. | should be clickable or not | as expected |  |  | Passed
TC-051 |  | functional |  | Remember me functionality works when checked |  | 1.go to url with browser 2. Click on "Sign In" button. 3. A new page will appear having Sign In button. | home page should be appeared | not working properly and not showing homepage | https://prnt.sc/Q0O4Ghk_sww3 https://prnt.sc/JqKMRGjMUOtw |  | Failed
TC-052 |  | functional |  | Checking password field is masked |  | 1.go to url with browser 2. Click on "Sign In" button. 3. A new page will appear having Sign In button. | Written password should be masked | as expected |  |  | Passed
TC-053 |  | functional |  | hovering the mouse should highlight the button |  | 1.go to url with browser 2. Click on "Sign In" button. 3. A new page will appear having Sign In button. | highlights the log in and sign up with fb button | as expected |  |  | Passed
TC-054 |  | functional |  | checking "forgot password" button | N/A | 1.go to url with browser 2. Click on "Sign In" button. 3. A new page will appear having Sign In button. | should lead to a recovery code page | as expected |  |  | Passed
TC-055 |  | positive |  | checking with valid email for reset password | anushkaazad6@gmail.com | 1.go to url with browser 2. Click on "Sign In" button. 3. A new page will appear having Sign In button. 4.click forgot password button 5.shows reset password page. | should send a code in email address | as expected |  |  | Passed
TC-056 |  | negative |  | checking with invalid email for reset password | anus@com | 1.go to url with browser 2. Click on "Sign In" button. 3. A new page will appear having Sign In button. 4.click forgot password button 5.shows reset password page. | should show an warning message | as expected |  |  | Passed
TC-057 |  | functional |  | copying password paste on text box | anu123456 | 1.go to url with browser 2. Click on "Sign In" button. 3. A new page will appear having Sign In button. 4.click forgot password button 5.shows reset password page. | should be accpectable | as expected |  |  | Passed
TC-058 |  | functional |  | Clicking "Registration" hyperlink | N/A | 1.go to url with browser 2. Click on "Sign In" button. 3. A new page will appear having Sign In button | registration UI should appear | as expected |  |  | Passed
TC-059 |  | functional |  | standard colour to identify the hyperlink | N/A | 1.go to url with browser 2. Click on "Sign In" button. 3. A new page will appear having Sign In button | should be standard colour to identify the hyperlink | as expected |  |  | passed
TC-060 |  | functional |  | clicking the hyperlink on mouse | N/A | 1.go to url with browser 2. Click on "Sign In" button. 3. A new page will appear having Sign In button | should be clickable the hyperlink by mouse | as expected |  |  | Passed
TC-061 |  | functional |  | ctrl + clicking the hyperlink | N/A | 1.go to url with browser 2. Click on "Sign In" button. 3. A new page will appear having Sign In button | should be open new tab after clicking the hyperlink | as expected |  |  | Passed
TC-062 |  | functional |  | checking hyperlinks validation | N/A | 1.go to url with browser 2. Click on "Sign In" button. 3. A new page will appear having Sign In button | should be no broken hyperlink | as expected |  |  | Passed
TC-063 |  | functional |  | checking hyperlink takes correct tab | N/A | 1.go to url with browser 2. Click on "Sign In" button. 3. A new page will appear having Sign In button | should take us to proper place | as expected |  |  | Passed
TC-064 |  | functional |  | checking hyperlink correct text | N/A | 1.go to url with browser 2. Click on "Sign In" button. 3. A new page will appear having Sign In button | should be correct text | as expected |  |  | Passed
TC-065 |  | functional |  | are correct message /warning message showed for password field | N/A | 1.go to url with browser 2. Click on "Sign In" button. 3. A new page will appear having Sign In button | should be showed warning message after giving vaild worng password | not found as expected |  |  | failed
TC-066 |  | functional |  | after clicking or selecting an option,dropdown should be highlighted. | N/A | 1.go to url with browser 2. Click on "Sign In" button. 3. A new page will appear having Sign In button | should be highlighted | as expected |  |  | passed
TC-067 |  | Non-Functional |  | score bar option if more option in the dropdown and few option are showed . | N/A | 1.go to url with browser 2. Click on "Sign In" button. 3. A new page will appear having Sign In button | should be all option showed | as expected |  |  | passed
TC-068 |  | Non-Functional |  | checking mouse cursor change according to ui element | N/A | 1.go to url with browser 2. Click on "Sign In" button. 3. A new page will appear having Sign In button | should be change according to UI element | as expected |  |  | Passed
TC-069 |  | Usability |  | application works on ios/android mobile | N/A | 1.go to url with browser 2. Click on "Sign In" button. 3. A new page will appear having Sign In button | should be works properly | as expected |  |  | passed
TC-070 |  | Browser Compatibility Testing |  | application works on browsers like google chrome, mozilla firefox. | N/A | 1.go to url with browser 2. Click on "Sign In" button. 3. A new page will appear having Sign In button | should be works properly | as expected |  |  | passed
|  |  | improvement | should add terms and privacy condition in registration
should add Eye icon on password field
should add captcha in log in section
should log in with email id or phone number
should sign up with google account

## Test Metrics
Testing Metrics
Area | Formula | Data | Percentage %
Excuted Test Cases | (Number of Excuted Test cases/Total number of test case written) X 100 | (70/70)X 100 | 100%
Not Excuted Test Cases | (Number of not Excuted Test cases/Total number of tests executed) X 100 | (0/70)X 100 | 0%
Passed Test Cases | (Number of Passed Test cases/Total number of executed test cases) X 100 | (60/70)X 100 | 85.71%
Failed Test Cases | (Number of Failed Test cases/Total number of executed test case) X 100 | (10/70)X 100 | 14.29%
Blocked test cases | (Number of Tase Case Blocked/ Total number of executed test case) X 100 | (0/70)X 100 | 0%
Defect density | (Number of defects found/Size(number of requrements)
Defect Leakege | (Number of defects found in UAT/number of defect found in test) X 100 | (0/0)X 100 | 0%
Defect Rejection | (Number of defect rejected/number of total defect found rasied) X 100 | (0/0)X 100 | 0%
DRE(Defect removal Efficiency) | (A/A+B) 100 Where, A means Defect ldentified/Fixed Defects, B means defect identified by customers/issued defects | 100 | 100%
Defect Age | Fixed date- Reported date | N/A | N/A

## Report
Test Case Report
Project Name - | Fabrilife
Module Name - | sign up,sign in |  |  |  |  | Total No. | Status | Result :
Test Case Version | - |  |  |  |  | 60 | PASS
Written By | anushka ,saddam,reem |  |  |  |  | 10 | FAIL
Executed By | anushka ,saddam,reem |  |  |  |  | 0 | Not Executed | New Features | Testing Scope | Testing Environment :
Reviewed By | - |  |  |  |  | 0 | Out of Scope |  |  | Test Environment | Google Chrome Browser
TEST EXECUTION REPORT
Test Case | PASS | FAIL | Not Executed | Out Of Scope | Total TC
| 60 | 10 | 0 | 0 | 70
Grand Total | 60 | 10 | 0 | 0 | 70
LIMITATIONS
Documents |  |  |  | Received | Useful
PRD |  |  |  | No | No
USER STORY |  |  |  | No | No
| Testing Type in Scope | Description
Yes/ No. Justification (If No): | Functional Testing | This type of testing ignores the internal parts and focuses only on the output to check if it is as per the requirement or not.
Yes/ No. Justification (If No): | Integration Testing | Testing of all integrated modules to verify the combined functionality after integration is termed as Integration Testing.
Yes/ No. Justification (If No): | Negative Testing | Testing having the mindset of “attitude to break” using incorrect data and invalid inputs.
Yes/ No. Justification (If No): | Usability Testing | Test application from user friendliness perspective.
Yes/ No. Justification (If No): | Browser Compatibility Testing | Browser Compatibility Testing is performed for web applications and it ensures that the software can run with the combination of different browser and operating system. This type of testing also validates whether web application runs on all versions of all browsers or not.
Yes/ No. Justification (If No): | Boundary Value Testing | There is an upper and lower boundary for each range and testing is performed on these boundary values.
Yes/ No. Justification (If No): | Risk Based Testing Or Regression Testing | Risk-Based Testing includes testing of highly critical functionality, which has the highest impact on business and in which the probability of failure is very high. Testing an application as a whole for the modification in any module or functionality is termed as Regression Testing.

## Bug Report
Bug Report
TC-012
Issue: do not reset the otp timer if user tries to register again changing the information on register option
Reproducing Steps:
1.go to url with broswer.
2.then login option comes with dropdown where 3 options come which is login, register, ordertrack.
3.register button click .
4. fill the fields with valid info.
5.Click on the Register button.
Env: Production
Module: Sign Up
Severity: P1
Bug Screenshot: | https://prnt.sc/lPHYR0joBOvU --> https://prnt.sc/dLeYVpr02x9j
Responsible QA: Anushka, Saddam, Reem